Kingfield Newsletter Schedule: June 2007 
Attendance: Thor Anderson, Martha Ingram, Joanna Hallstrom
The Newsletter Committee met on April 19th and developed the following article list and publishing schedule.

| Task | Day | Date | Instructions |
| --- | --- | --- | --- |
| Newsletter Meeting - time 7:00pm Caffe Tempo | Thursday | April | 19 | 2 weeks to write articles |
| Confirm Article Assignments | Friday | April | 20 | KFNA emails committee article assignment list |
| Article Due Date – by 12:00 noon | Friday | May | 4 | Writers email articles to KFNA@qwest.net by 12:00 noon / KFNA submits compiled articles to Editor |
| Edited Material Reviewed | Monday | May | 7 | Editor turns in edited articles to KFNA / KFNA reviews edits /pass any changes through editor |
| Articles Submitted For Layout | Thursday | May | 10 | Editor emails compiled articles to Graphic Designer for Layout |
| First Review of Layout | Monday | May | 14 | Graphic Designer returns layout to KFNA and Editor, layout reviewed, KFNA compiles changes, one hard copy submitted to Editor |
| Changes to Layout Turned In | Tuesday | May | 15 | Editor reviews changes and drops off hard copy to Graphic Designer to make changes |
| Final Review of Layout Proof | Wednesday | May | 16 | Graphic Designer emails final PDF to KFNA for final review / any changes back to Graphic Designer |
| Final Draft To Printer | Friday | May | 18 | Graphic Designer emails final PDF to printer and reviews printer proof (5 business days to print) |
| To Bulk Mail Distributor | Thursday | May | 24 | Cooperative Printing delivers newsletter to DoGood.Biz |
| Mail Date | Tuesday | May | 29 | Direct Mail Drop – 3 to 5 day delivery period |
| Arrive In Kingfield Homes | Thursday | June` | 1 | 3 to 5 day delivery period |

| Article List | Back Up article: |
| --- | --- |
| Annual Meeting Report / KFNA New Board Member Introduction - Martha | Name the BRT station if the time frame coincides - Darrel |
| Block Club Article: Van Nest Block Building Award - Jacqueline |  |
| Community Engagement – Neighborhood Response – Mark Hinds | Event List |
| BFIP Updates- which businesses are receiving grant – Tom Parent | Farmers’ Market Opening June 3 / Second Sunday Schedule |
| Summer Soccer / Park Programs – small article – Joanna to get dates from Brian Cornell | HHD June 23 |
| 2007 Business Sponsor List - Sarah | Walldogs September 13-16 |
| Wall Dogs Where and What - Sarah | National Night Out Tuesday, August 7 |
| Festival – small announcement - Joanna / Brian Cornell | Summer Festival Thursday, July 19 |
| HHW Drop Day – small announcement – Darrel or Dave | Summer Soccer / MLK Programs |
| Dodgeball Recap – Thor to take photo / Sarah Larger Caption |  |
| Farmers’ Market |  |
| New Coordinator / Ice Cream Contest / New Add Campaign (image)- Joanna |  |
| Opening Event / vendor highlights / Band list – Deborah Bourne | Photo List / Artwork |
| ImproveGroup grant / web design for market - Sarah | Art to /DI/ For Photo with caption |
| Stormwater map and brief description Darrel or Dave | BFIP Photo of new work |
| Delay of the Lyndale Project Matt Perry | Farmers’ Market “We are Growing” add |
| Art to DI for - small recap - Sarah | NEHBA Logo |
| New Business Articles: Grand Café / Sundays for KFNA – Thor | Dodge Ball Photo |
| Nicollet-East Harriet Update / Logo – Matt Perry (tweek March article) | New Board Photo |
| MLK Fence Issue and Compromise: Jay Walljasper |  |

# Text boxes

Quarterly Editions
 (3rd month of quarter)

2007 Mail Dates

March  15

June 1
September 1

December  1